## MCM
Risk ID | Category | Risk Description | Probability | Impact | Risk Score | Mitigation Strategy | Indicator | Contingency Plan | Responsible | Status | Last modifed date
1 | Organization | Key team member leaves the project unexpectedly | 3 | 10 | 30 | Hope, cry, learn hard, good documentation, cry more | Compilerbau Exam! | cry; try to understand the documentation | Prof. Dr. Vollmer (Compiler-King) | Open | 2023-04-13
2 | Project | Personal development equipment failure | 1 | 4 | 4 | Version control via GitHub | hardware malfunction | Use a different hardware, restore the data from Git | Developer | Open | 2023-04-13
3 | Business | Change of 3rd Party Licences | 1 | 6 | 6 | File a contract with the developers | Public notice | Change to a different library | Legal Counsel | Open | 2023-04-13
4 | Technical | Code injection (security) | 4 | 10 | 40 | Filter inputs to catch malicious inputs | Injection from Script Code into the application | Shutdown service, notify developers, restore pre attack version and release hotfix | IT manager | Open | 2023-04-13
5 | Technical | Hardware unavailable | 1 | 10 | 10 | Strategies for a diversity of the platform (Different devices) | Chip-Shortage, hardware eol (end of life) | Change to a different available platform | IT manager | Open | 2023-04-13
6 | Technical | Hardware resources | 5 | 10 | 50 | Change to more powerful hardware; Optimise Performance | Hardware runs out of memory and cpu resources (because of to many users and messages) | Limit user | IT manager | Open | 2023-04-13
Probability: 1 - 5
Impact: 1 - 10
Risk Score = Probability * Impact

## Vorlage
Risk ID | Category | Risk Description | Probability | Impact | Risk Score | Mitigation Strategy | Indicator | Contingency Plan | Responsible | Status | Last modifed date
1 | Organization | Key team member leaves the project unexpectedly | 3 | 10 | 30 | Develop attractive compensation packages, offer professional development opportunities, and foster a positive work culture | Often absence; depressed team atmosphere | Conduct exit interviews, establish talent pipelines, and provide onboarding support to new employees | Group leader | Open | 2023-04-02
2 | Project | Vendor delays delivery of critical components | 5 | 9 | 45 | Maintain alternative suppliers, diversify supplier base, and establish clear contracts and performance standards | Slow status update | Implement emergency inventory management procedures, source alternative suppliers, and expedite delivery times | Procurement Manager | Open | 2023-04-02
3 | Project | Equipment failure during critical production cycle | 2 | 6 | 12 | Conduct regular maintenance and inspection of equipment to identify and fix any issues before they result in equipment failure. | Errors in log report; weird behavior; over heating | Establish clear communication protocols to ensure all relevant personnel are notified in the event of equipment failure. Develop a plan for quickly repairing or replacing failed equipment to minimize production downtime. | Operations manager | Closed | 2023-04-04
4 | Legal | Unexpected changes in government regulations | 3 | 4 | 12 | Monitor regulatory changes, establish policies and procedures for compliance, and conduct regular training sessions | Discussions in public media | Respond promptly to regulatory inquiries, establish internal review procedures, and implement corrective actions as necessary | Legal Counsel | Open | 2023-04-05
5 | Business | Budget cuts reduce funding for project | 5 | 10 | 50 | Prioritize project deliverables to ensure that critical objectives are met even in the event of budget cuts. | Bad annual financial reports; reorganization; change of managers | Communicate the budget cut to all project stakeholders and establish a clear plan for managing expectations. Establish clear criteria for making decisions about which activities to cut or reduce. | Project manager | Closed | 2023-04-06
6 | Organization | Natural Disaster | 1 | 10 | 10 | Conduct regular safety drills, establish evacuation routes, and ensure all employees are trained in emergency response procedures | Extrem weather | Identify safe areas for evacuation, establish communication protocols, and maintain an emergency kit with essential supplies | Operations manager | Open | 2023-04-06
7 | Technical | Cyber Attack | 5 | 10 | 50 | Implement regular software updates, install firewalls and antivirus software, and restrict access to sensitive data. Use https. | Data exfiltration and remote communications from criminal servers. Internal hosts communicating with countries outside of business range. | Identify and isolate infected systems, report the incident to the appropriate authorities, and restore systems from backups if necessary | IT manager | Open | 2023-04-06
8 | Technical | Bad performance of new technique | 3 | 8 | 24 | Conduct a thorough analysis of the technique and identify potential issues that may impact its performance. | Test set XYZ fail. | Establish clear criteria for making decisions about whether to continue using the technique or switch to an alternative. Develop a plan for communicating with project stakeholders about the performance issue and its impact on the project. | Senior project member | Open | 2023-04-02